Prepared for:

Dr. Dean Lacy

Professor of Political Science

The Ohio State University

FIELD REPORT

2002 TOPS (The Ohio Political Survey) Project

Prepared by:

Matthew W. Courser, M.A.

Research Associate

with

Chia-Hung Tsai

Center for Survey Research

College of Social and Behavioral Sciences

### The Ohio State University

## January 2003

Project Staff:

###### Matthew W. Courser, M.A., Project Director

Chia-Hung Tsai, M.A., Senior Graduate Research Associate

Daniel Hoechst, Graduate Research Associate

- Purpose

This field report presents the methodological details for a national telephone survey conducted in November and December 2002 by the Center for Survey Research (CSR) at The Ohio State University.  The Principal Investigator for this project was Dr. Dean Lacy, a Professor of Political Science at Ohio State University.

This study had two purposes.  First, the study used data from an RDD sample of Ohio residents to measure Ohioans’ voting behavior and political attitudes immediately after the 2002 national elections.  A second part of the 2002 TOPS study used a panel design to re-contact respondents first interviewed just before the election.

- Questionnaire Development and Support Materials

The Principal Investigator developed the questionnaire used in this study in consultation with the CSR project staff, and with Dr. Gerald Kosicki, CSR’s Faculty Director.

Questions in the first section focused on respondents’ evaluations of George W. Bush, other national political figures, and political institutions in Ohio and at the national level.  The second section asked respondents whether they voted, how they voted, and who they voted for in both national and state-level elections.  Respondents then were asked a series of questions that focused on their own ideological predispositions, along with their attributions of the ideologies of a variety of political figures.  Questions in the following section provided respondents with a series of adjectives and asked respondents how well each described a variety of political figures.  Respondents in the panel sample then were asked whether they went online to get information, and also were asked for their position on a variety of issues facing the state of Ohio.  Questions in the next section were administered to all of the respondents and asked them for their opinions on a number of gender-related issues.  Following those questions, respondents received a series of questions that presented alternative and mutually exclusive policy proposals in each questions and which asked respondents which they favored.   Following those questions, respondents in the RDD sample received an extensive battery of questions focused on U.S. foreign policy.  The final section included a brief series of standard demographic questions.  The order and wording of questions were randomized in various places in the instrument to help control for question order and question wording effects.

##### Interviewers were provided with extensive support material, including scripted introductions designed to help them gain the cooperation of respondents and detailed fallback statements to help them answer questions that respondents were likely to ask (see Appendix).

- CASES Programming, Pilot Testing and Questionnaire Timing

The questionnaire was programmed into the computer-assisted telephone interviewing (CATI) system at CSR, which uses the CASES software distributed by the University of California at Berkeley.  (The programmed questionnaire syntax is located in an appendix to this report).

The programming for the questionnaire was fairly extensive and had to be completed in a fairly short time frame.  As a result there were a number of  programming-related issues that later impacted the integrity of the data.  First, it was discovered after ten completed interviews that the item thanking respondents for completing the interview process was being skipped.  This was corrected after the first shift of interviewing. Additionally, on November 11 it was discovered that after respondents question d3 they were being skipped over questions hm2-hm5.  Additionally, due to confusion between the Client and CSR, a programming change was made on Novmber 12 to ensure that everyone in the sample received questions P1 through P6, SC1 through SC4, and KS1—not just the RDD respondents.

Additionally, it was discovered that the RDD version of the questionnaire was taking, on average, significantly longer to administer than the 30 minutes budgeted for the project.  On November 15, questions VOTEHOW, VOTETYPE, VOTEEASY, VOTEFAIR, PVOTE00, P1, P3, SC3, and SC4 were cut from both the RDD and panel questionnaires.  Because questions P1, P3, SC3, and SC4 were important to the research program of Dr. Kosicki, one of the co-Principal Investigators on this project, those questions were added back into the panel instrument on November 18.  Additionally, CSR developed a callback sequence and called back the 66 cases on the panel sample that were skipped due to this cut.  52 of the 66 (or 78%) resulted in a successfully completed callback interview.

- Interviewer Training and Monitoring

- Project Training

A demographically diverse group of 60 interviewers and 16 supervisors were trained for, and worked on, this project.  Both groups of CSR employees received extensive training before working on this project that included:

- Formal training sessions conducted by the Project Director, the Principal Investigator, and/or project GRAs to brief interviewers in detail about the project and the instrument.  These sessions averaged one hour in length and were conducted in a classroom setting.

- Formal training sessions for supervisors that briefed them on the survey instrument and which detailed their responsibilities as supervisors on this project. These sessions, on average, were half an hour long.

- Written training instructions and background materials for interviewers and supervisors to review prior to engaging in practice interviews.  These training materials included background information such as:  (1) the purpose and goal of the study; (2) the sponsor of the project; (3) how the sample was drawn; (4) who qualified as an eligible respondent; and (5) the total number of completed interviews needed and the projected length for the field period.  Written training instructions highlighted key parts of the questionnaire that contained important, new, or difficult elements, and item-specific instructions and skip patterns were noted.  These instructions and background materials are located in an appendix to this report.

- Self-directed training using a computerized practice version of the questionnaire programmed in CASES.  Interviewers were required to complete at least two practice cases, and supervisors and project staff were available to answer questions from interviewers as they completed this self-directed training process.  Depending on the needs of individual interviewers, these self-directed training sessions ranged from 90 minutes to two hours in length.

- On-the-job interviewer and supervisor training continued throughout the field period via daily monitoring by, and memos from, the project management staff.

C. Monitoring

Both interviewers and supervisors were monitored continuously throughout the project.  Interviewers were monitored unobtrusively via a remote telephone during the interviewing process by the supervisor on duty or by project staff.  Corrective feedback was given as needed by the supervisor on duty, and a formal written rating sheet was completed for individual interviewers during every monitoring session.  This rating sheet was then given to administrative staff who reviewed it for problems needing immediate attention.  Staff followed up with individual interviewers as needed and worked intensively with interviewers who had difficulty with the questionnaire.  Interviewers who continued to struggle and/or who did not perform adequately after the intensive interaction were removed from the project and re-assigned to other work.

Supervisors also were monitored continuously throughout the project.  Contact was made on a daily basis among the Project Director, the research associates, and the supervisors in person, by telephone, and/or via memos.  Supervisors were encouraged to contact the project director with any ambiguities and concerns related to the project.  These measures assured that there is ongoing communication among those working on the project.

- Interviewing

The fieldwork was conducted between November 8, 2002 and December 12, 2002.  Weekday interviewing generally started at 12:30 p.m. EDT and ended at 9:30 p.m. EDT.  Saturday shifts lasted from 10:30 a.m. to 4:30 p.m. EDT, and Sunday shifts from 5:30 p.m. to 9:30 p.m. EDT.

- Incentives and Bonus Pay

In order to maximize the productivity of CSR’s professional interviewing staff and the quality of the data gathered throughout the project, CSR provided significant monetary incentives and bonus pay to the interviewers and supervisors who worked on this project.  All of the incentives were included in the total cost of the project and were provided at no additional cost to the client.

#### A.  Incentives per completion

CSR’s ongoing incentive program provides wooden tokens, called “CSR Half-Bucks,” to interviewers for each interview they completed.  After interviewers accumulated a sufficient number of these Half-Bucks, they could then exchange the tokens for gift certificates for gift certificates to a variety of local merchants (such as Wendy’s and Kroger).  CSR awarded two (2) Half-Bucks per completed interview on the 2002 TOPS Survey.

#### B.  Incentives per refusal conversion

Because refusal conversions usually are more difficult than normal completions, CSR provided more Half-Bucks for each refusal conversion completion than for each regular completion.  Interviewers were rewarded with four (4) Half-Bucks for each refusal they converted successfully.

- Sampling and Within-Household Respondent Selection

#### A.  Sampling Pools

This project utilized two samples of Ohio residents.  For the RDD sample, CSR utilized a random-digit dial frame of the entire state of Ohio.  This was purchased from Genesys Sampling Systems, Inc., using their procedures whereby any local prefix in the state with at least one listed telephone number had a nonzero chance of being used to generate a RDD telephone number in the sampling pool.  Genesys Sampling Systems, Inc., also purged many non-residential and non-working numbers from the sample using their ID-plus procedure.

In general, the RDD approach to telephone sampling ensures that any household in a designated geographic area (e.g. all 50 states) that has a telephone, regardless of whether or not the telephone number is listed or unlisted, may be sampled for participation.

The panel sample consisted of the 342 respondents who completed a pre-election interview and who agreed to be re-interviewed after the November election.  Because these respondents, as part of their consent, provided their names, CSR trained interviewers to pursue these respondents at whatever alternate telephone numbers they were able to obtain for the respondents.

#### B.  Within-Household Respondent Selection

For each household we contacted in the RDD sample, interviewers were trained to select the proper respondent using the “last birthday method.”  In general, eligible respondents were those who spoke English, who were 18 years of age or older, and who were physically and mentally capable of being interviewed.

Because we knew the name of the vast majority of respondents in the panel sample, interviewers were trained to ask for that person by name when starting their introductions.  If the named respondent was not available and/or not living at the number we had for him/her, interviewers were trained to probe for new contact information for the named respondent.  If a new telephone number was available, interviewers then pursued the respondent at the new number.

The introductory script (and within-household respondent selection procedures) for the RDD sample and a template of the same materials for the list sample are included in an Appendix volume to this report.

- Callbacks

In processing the sample for this study, at least 20 dialing attempts were allowed to reach eligible households to complete interviews.

Table 1 details the callback information for the 810 completed interviews.  The Project Director and Project GRAs worked to ensure that the sample was managed efficiently and that hard-to-reach households were attempted on different days of the week and at a variety of times during the day and evening hours.  Table 2 presents the same information for all 3,143 numbers used in the sampling pools for this study.

Tables 1 and 2 demonstrate that some of the interviews required more than 40 dialings to complete.

# Disposition of the Sampling Pool

A total of 810 interviews were completed on both samples as part of the TOPS project.  Interviewing commenced on November 8, 2002 and ended on December 12, 2002.  Overall, 3,143 numbers were released (dialed) from the sampling pools (see Table 2), and over 22,700 call attempts were made by CSR interviewers to complete interviews.

Tables 3 and 4 present the final sample dispositions for the national sample and the oversample on this project.

The pattern of final dispositions in the sampling pool was quite similar to what could be expected in an RDD survey that employs numerous callbacks and active sample management (see Lavrakas, 1993, pp. 81-94).

- Response Rates and Cooperation Rates

As shown below, there are different denominators that can be used in calculating the overall response rate for each of the samples that were used as part of this project.  The rates presented below are designed to conform to AAPOR’s Standard Definitions:  Final Dispositions of Case Codes and Outcome Rates for Surveys (2000 edition).

- Response Rates for RDD sample

  - AAPOR Response Rate 1:  Using the 2,032 possibly eligible households as the comparison, the 552 completions represent a 27 percent response rate.

  - AAPOR Response Rate 5:  Using the 552 completions as the numerator and the 1,282 known-eligible households as the denominator provides a 43 percent response rate.

- Response Rates for Panel Sample

  - AAPOR Response Rate 1:  Using the 326 possibly eligible households as the comparison, the 260 completions represent an 80 percent response rate.

  - AAPOR Response Rate 5:  Using the 260 completions as the numerator and the 307 known-eligible households as the denominator provides a 85 percent response rate.

- Cooperation Rates for RDD Sample

  - AAPOR Cooperation Rate 3:  Comparing the 552 completions with the 1,256 cases categorized as completions, household refusals, respondent refusals, partials/partial refusals, and double refusals yields a 44 percent completion rate, or what is sometimes referred to as a “cooperation rate.”

  - Modified AAPOR Cooperation Rate 3:  Taking into account all households in which it is certain that an interviewer spoke with the selected respondent (n=744; all completions, respondent refusals, and respondent partials), the cooperation rate was 74 percent.

- Cooperation Rates for Panel Sample

  - AAPOR Cooperation Rate 3:  Comparing the 260 completions with the 283 cases categorized as completions, household refusals, respondent refusals, partials/partial refusals, and double refusals yields a 92 percent completion rate, or what is sometimes referred to as a “cooperation rate.”

  - Modified AAPOR Cooperation Rate 3:  Taking into account all households in which it is certain that an interviewer spoke with the selected respondent (n=271; all completions, respondent refusals, and respondent partials), the cooperation rate was 96 percent.

- Partial Completions

There were a total of 140 cases that were partial completions at some point during the interviewing process.  The CSR Project Director worked aggressively to ensure that partial completions and partial refusals were re-contacted at appropriate times.  As a result of these efforts, 98 of the 140 (or approximately 70 percent) partial and partial refusals ended in a completed interview.

- Refusal Conversions

Refusal conversion efforts began on November 26, 2002, and were managed systematically by the Project Director.  Project staff and senior administrative staff reviewed callsheets and refusal report forms on a daily basis and selected household refusals for conversion attempts if the refusal report form indicated that the household might reasonably be converted.  “Hard” refusals, or those in which a member of the household asked us not to call back were not attempted, and at least five days had to elapse between the initial refusal and the beginning of our conversion efforts.  After November 26, 2002, at least one interviewer per shift was assigned to work on refusal conversion callsheets.

Conversion efforts led to 73 successful refusal conversions, representing 9.0 percent of the total completed interviews.

## Appendix Volume

As part of this report, an Appendix volume that contains other detailed information about the work that was conducted.

The Appendix volume contains:

- Frequencies for each variable in the post-election data set

- History files detailing open-ended responses from each questionnaire

- The actual questionnaire administered to respondents

- Support materials for interviewers

- Bibliography

American Association for Public Opinion Research.  (2000)  Standard Definitions: Final Dispositions of Case Codes and Outcome Rates for Surveys.  Ann Arbor, MI.

Lavrakas, Paul J.  1993.  Telephone Survey Research Methods:  Sampling, Selection, and

Supervision, Vol. 7.  Thousand Oaks, CA:  Sage Publications.

Table 1:  Number of call attempts for completed cases (n=810)

| Call Attempts | Frequency | Percent |
| --- | --- | --- |
| 1 | 178 | 22.0% |
| 2 | 148 | 18.3% |
| 3 | 103 | 12.7% |
| 4 | 76 | 9.4% |
| 5 | 74 | 9.1% |
| 6 | 41 | 5.1% |
| 7 | 37 | 4.6% |
| 8 | 18 | 2.2% |
| 9 | 22 | 2.7% |
| 10 | 15 | 1.9% |
| 11 | 13 | 1.6% |
| 12 | 10 | 1.2% |
| 13 | 13 | 1.6% |
| 14 | 6 | 0.7% |
| 15 | 7 | 0.9% |
| 16 | 10 | 1.2% |
| 17 | 7 | 0.9% |
| 18 | 6 | 0.7% |
| 20 | 6 | 0.7% |
| 21 | 2 | 0.2% |
| 22 | 4 | 0.5% |
| 23 | 3 | 0.4% |
| 24 | 5 | 0.6% |
| 26 | 1 | 0.1% |
| 27 | 1 | 0.1% |
| 30 | 1 | 0.1% |
| 32 | 2 | 0.2% |
| 33 | 1 | 0.1% |
| TOTAL | 810 | 100.0% |

Table 2:  Number of call attempts for all cases (n=22,746)

| Call Attempts | Frequency | Percent |
| --- | --- | --- |
| 1 | 861 | 27.4% |
| 2 | 436 | 13.9% |
| 3 | 278 | 8.8% |
| 4 | 240 | 7.6% |
| 5 | 174 | 5.5% |
| 6 | 120 | 3.8% |
| 7 | 119 | 3.8% |
| 8 | 81 | 2.6% |
| 9 | 78 | 2.5% |
| 10 | 57 | 1.8% |
| 11 | 57 | 1.8% |
| 12 | 57 | 1.8% |
| 13 | 48 | 1.5% |
| 14 | 40 | 1.3% |
| 15 | 31 | 1.0% |
| 16 | 39 | 1.2% |
| 17 | 21 | 0.7% |
| 18 | 27 | 0.9% |
| 19 | 19 | 0.6% |
| 20 | 36 | 1.1% |
| 21 | 15 | 0.5% |
| 22 | 15 | 0.5% |
| 23 | 22 | 0.7% |
| 24 | 15 | 0.5% |
| 25 | 7 | 0.2% |
| 26 | 10 | 0.3% |
| 27 | 16 | 0.5% |
| 28 | 13 | 0.4% |
| 29 | 23 | 0.7% |
| 30 | 145 | 4.6% |
| 31 | 12 | 0.4% |
| 32 | 6 | 0.2% |
| 33 | 1 | 0.0% |
| 34 | 1 | 0.0% |
| 35 | 2 | 0.1% |
| 37 | 1 | 0.0% |
| 38 | 2 | 0.1% |
| 40 | 3 | 0.1% |
| 41 | 4 | 0.1% |
| 42 | 2 | 0.1% |
| 43 | 1 | 0.0% |
| 44 | 3 | 0.1% |
| 46 | 1 | 0.0% |
| 47 | 1 | 0.0% |
| 48 | 1 | 0.0% |
| 51 | 1 | 0.0% |
| 60 | 1 | 0.0% |
| Total | 3143 | 100.0% |

Table 3:  Final Disposition of Sampling Pool--RDD Sample

Ineligible						Freq	Pct of Total

Not a resident of sample area			       6	  0.22%

No adult member of HH 				       7	  0.26%

Non-residential number				   325	11.86%

TEMPORARY disconnect			     50	  1.82%

Non-working number				   245	  8.94%

Number (prefix/suffix) changed			     33	  1.20%

Area code changed				       0	  0.00%

Number changed				       0	  0.00%

Miscellaneous					     66	  2.41%

Sub-total Ineligible: 				   732

Pre-selection

HH Refusal					   327  11.93%

No Contact made w/ HH				   381	9.60%

Answering machine				   131	4.78%

HH/Caller ID privacy manager			     42	1.53%

Non-English speaking HH			     12	0.44%

Sub-total Pre-Selection			 	   893

Post-selection

Specific appointment				     67	2.44%

General callback/R unavailable 			   138	5.03%

Completed Interview				   552  20.13%

Respondent refusal				   153	5.58%

Double refusal					   186    6.64%

Physical/mental incapacity			     25	0.91%

R unavailable during field period			     17	0.62%

Partial interview					     38	1.38%

Non-English speaking R				       0	0.00%

Sub-total Post-Selection 			 1,176

Total Activated						 2,801  	100.00%

Table 4:  Disposition of Sampling Pool—Panel sample

Ineligible							Freq	Pct. of Total

Not a resident of sample area				      0	  0.00%

No adult member of HH 					      0	  0.00%

Non-residential number					      1	  0.29%

TEMPORARY disconnect				      3	  0.87%

Non-working number					      2	  0.58%

Number (prefix/suffix) changed				      1	  0.29%

Area code changed					      0	  0.00%

Number changed					      2	  0.58%

Miscellaneous						      5	  1.46%

Sub-total Ineligible					     14

Pre-selection

HH Refusal						      12	   3.51%

No Contact made w/ HH					        7	   2.05%

Answering machine					      24	   7.02%

HH/Caller ID privacy manager				        0	   0.00%

Non-English speaking HH				        0	   0.00%

Sub-total Pre-Selection					       43

Post-selection

Specific appointment					       4	   1.17%

General callback/R unavailable 				       7	   2.05%

Completed Interview					   260	 76.02%

Respondent refusal					     10	   2.92%

Physical/mental incapacity				       2	   0.58%

R unavailable during field period				       1	   0.29%

Partial interview						       1	   0.29%

Non-English speaking R					       0	   0.00%

Sub-total Post-Selection					   285

Total Activated							   342   100.00%